## Year1&2
Project Implementation Plan
Project Title | Developing Land Management Options for Diverse Cacao-based system in Mindanao | [41 empty] | Planned | [47 empty] | Planned
Proponent(s) | [42 empty] | Progress | [47 empty] | Progress
Date of Project Start | 2022-08-04 | [41 empty] | Delayed | [47 empty] | Delayed
Date of Update | 2024-07-31 | [41 empty] | Completed | [47 empty] | Completed
[5 empty] | Year 1 | [47 empty] | Year 2
Amount Spent |  |  |  |  | 2022 |  |  |  | 2022 |  |  |  | 2022 |  |  |  | 2022 |  |  |  | 2022 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2023 |  |  |  | 2023 |  |  |  | 2023 |  |  |  | 2023 |  |  |  | 2023 |  |  |  | 2023 |  |  |  | 2023 |  |  |  | 2023 |  |  |  | 2023 |  |  |  | 2023 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2024 |  |  |  | 2024 |  |  |  | 2024 |  |  |  | 2024 |  |  |  | 2024
Output | Activity and Task | Start | End | Progress (%) | July |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | June
[5 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Output 1.1 | Activity 1.1.1 | 2022-08-05 | 2023-05-31
Task 1 - PPMP & hiring | bar: July 1 to Aug 4
Task 2 - PR | bar: Sep 1 to Sep 2
Task 3 - Bidding and Reciept | bar: Sep 3 to May 4
| Activity 1.1.2 | 2022-08-16 | 2022-12-31
Task 1 - Coordination with Coop/farmers | bar: Aug 3 to Sep 4
Task 2 - Designing of the experimental site | bar: Oct 2 to Nov 1
Task 3 - Lay-outing and application of treatments in the sites; and mentoring of farmer-cooperators | bar: Nov 2 to Dec 4; May 1 to May 4
| Activity 1.1.3 | 2023-01-01 | 2023-12-31
Task 1 - Regular site monitoring | bar: Jan 1 to June 4
Task 2 - Gathering of data and samples; and mentoring of farmer-cooperators | bar: Feb 1 to Apr 4
Task 3 - laboratory analysis of samples | bar: Mar 1 to May 4
Task 4 - Analysis and interpretation of initial data | bar: May 3 to June 2
Output 1.2 | Activity 1.2.1 | 2024-01-01 | 2024-06-30
Task 1 - scouting of journal/ publisher
Task 2 - packaging of the article
| Activity 1.2.2 | 2024-03-01 | 2024-06-07
Task 1- -submission of the article
Task 2 - responding to comments and review of the editors
Ouput 2.1 | Activity 2.1.1 | 2022-08-01 | 2022-10-07
Task 1- coordination and scheduling with GGGI expert | bar: Aug 1 to Aug 4
Task 1-Preparation and conduct of online session on good land management practices with GGGI expert | bar: Sep 1 to Oct 1
| Activity 2.1.2 | 2024-01-05 | 2024-02-15
Task 1- Coordination with coop representative and partners
Task 2-Formulation of workshop design
Task 3-Conduct of workshop
Task 4-Packaging of training materials and IEC
| Activity 2.1.3 | 2024-01-05 | 2024-02-21
Task 1- procurement of printing materials
Task 2- printing
Ouput 2.2 | Activity 2.2.1 | 2024-03-01 | 2024-03-15
Task 1- coordination
Task 2-conduct of planning and scheduling workshop
| Activity 2.2.2 | 2024-03-01 | 2024-05-31
Task 1- procument of training materials, food and venue
Task 2-conduct of knowledge sharing sessions
Project Monitoring and Evaluation | Task 1 - Submission of inception report | bar: July 4
Task 2 - Submission of monitoring report | bar: Sep 4; Dec 3; Mar 4; June 3
Task 3- Submission of Year-end progress report | bar: June 4
Task 4-Submission of Terminal report